## Sheet1
Date	Time	Activity
29/10/2018	3	Raspberry pi setup
31/10/2018	2	Oupa house getting data
03/11/2018	2	Grafana and InfluxDB
05/11/2018	1	Python USB
08/11/2018	0.5	Python InfluxDB
10/11/2018	1.5	Logging, scheduler, interface info
06/01/2019	2	Test data
11/01/2019	0.5	Influx DB
17/01	1.5	Influx DB
19/01	2	Status and mode to DB
20/01	1	Ratings to DB
20/01	0.5	Grafana
23/01	1	Grafana
24/01	2	Grafana (0.5), UI
26/01	6	Grafana and config (1), USB reading 5
27/01	4	Threading, UI
28/01	1	GUI
29/01	0.5	Commands sending
30/01	1.5	GUI
31/01	2	DB query time report
19/02/02	1	Spreadsheet creation
2019-03-03	2	Spreadsheet creation
2019-03-16	3	Oupa debugging. At least got the USB permissions working. CRC failures for mode and pigs
2019-03-21	1	CRC 0.5, Flask 0.5
2019-03-28	1	Flask
2019-03-31	1	Vue.js installation and fault find
2019-04-02	1	Npm, Node and Vue installation
2019-04-03	0.5	Vue example
2019-04-09	0.5	Vue example
2019-12-04	1.5	Postgres, Django, Remote.it
2019-12-05	1	Django DB config
2019-12-07	2	Python upgrade
2020-02-16	2	Pi4 installation
2020-02-18	1	Watchpower on Linux
2020-02-19	1	Watchpower on Pi
2020-02-21	1	Python VM: Django
2020-02-23	1	Python VM: Grafana and InfluxDB
2020-02-23	1	Python VM: Redis and Celery
2020-02-25	0.5	Logging, reboot of grafana
2020-02-26	1.5	Installation on Pi4: project, Django, Influx, Grafana
2020-02-27	1	Installation on Pi4: Celery, Redis, all running
2020-02-29	2	Remote.it, nginx and gunicorn
2020-03-17	1	Python script as a service
2020-03-18	3	Oupa dashboards, alerts